## Sheet1
task_id | task_name | assigned_role | priority | time_days | budget | dependencies
T001 | Project Planning & Scope Definition | Project Manager | High | 10 | 5000 | []
T002 | Infrastructure Setup | DevOps Engineer | High | 15 | 7500 | ['T001']
T003 | Knowledge Base Integration Strategy | Solution Architect | High | 10 | 6000 | ['T001']
T004 | NLP Model Design & Architecture | AI/ML Engineer | High | 20 | 12000 | ['T001', 'T003']
T005 | Data Collection & Preprocessing | Data Engineer | Medium | 25 | 10000 | ['T003']
T006 | NLP Model Training & Evaluation | AI/ML Engineer | High | 30 | 15000 | ['T004', 'T005']
T007 | Chatbot Core Logic Development | Backend Developer | High | 25 | 12500 | ['T002', 'T004']
T008 | Knowledge Base API Development | Backend Developer | Medium | 20 | 10000 | ['T003', 'T007']
T009 | User Interface (UI) Development | Frontend Developer | Medium | 30 | 15000 | ['T007']
T010 | Admin Interface Development | Full Stack Developer | Medium | 25 | 12500 | ['T007', 'T008']
T011 | System Integration | Full Stack Developer | High | 15 | 7500 | ['T006', 'T008', 'T009', 'T010']
T012 | Comprehensive Testing (Unit, Integration, UAT) | QA Engineer | High | 20 | 10000 | ['T011']
T013 | Deployment Strategy & Execution | DevOps Engineer | High | 10 | 5000 | ['T002', 'T012']
T014 | Monitoring & Feedback Loop Implementation | DevOps Engineer | Medium | 15 | 7500 | ['T013']