## Sheet1
task_id | task_name | assigned_role | priority | time_days | budget | dependencies
T001 | Overall System Architecture Design | Solution Architect | High | 7 | 3500 | []
T002 | Database Schema Design and Implementation | Backend Developer | High | 10 | 5000 | ['T001']
T003 | Develop User Registration & Authentication API | Backend Developer | High | 8 | 4000 | ['T002']
T004 | Develop Restaurant & Menu Management API | Backend Developer | High | 12 | 6000 | ['T002']
T005 | Develop Order Placement & Status Management API | Backend Developer | High | 15 | 7500 | ['T002', 'T003', 'T004']
T006 | Integrate Secure Payment Gateways API | Backend Developer | High | 10 | 5000 | ['T005']
T007 | Develop Real-time GPS Tracking API & Integration | Backend Developer | High | 14 | 7000 | ['T005']
T008 | Develop Rating and Review System API | Backend Developer | Medium | 7 | 3500 | ['T003', 'T004', 'T005']
T009 | Design Customer User Interface (Web & Mobile) | UI/UX Designer | High | 15 | 7500 | ['T001']
T010 | Design Restaurant Dashboard User Interface | UI/UX Designer | High | 10 | 5000 | ['T001']
T011 | Design Driver Application User Interface | UI/UX Designer | High | 8 | 4000 | ['T001']
T012 | Develop Customer Mobile Application (iOS & Android) | Mobile Developer | High | 30 | 15000 | ['T003', 'T004', 'T005', 'T006', 'T007', 'T008', 'T009']
T013 | Develop Restaurant Web Dashboard | Frontend Developer | High | 20 | 10000 | ['T003', 'T004', 'T005', 'T010']
T014 | Develop Driver Mobile Application (iOS & Android) | Mobile Developer | High | 25 | 12500 | ['T003', 'T005', 'T007', 'T011']
T015 | Cloud Infrastructure Setup & CI/CD Pipeline | DevOps Engineer | High | 15 | 7500 | ['T001']
T016 | Security Audit and Data Privacy Compliance Implementation | Security Engineer | High | 10 | 5000 | ['T003', 'T006']
T017 | Comprehensive System Testing (Functional, Performance, Security) | QA Engineer | High | 20 | 10000 | ['T012', 'T013', 'T014', 'T006', 'T007']
T018 | System Deployment, Monitoring, and Post-launch Support Setup | DevOps Engineer | High | 7 | 3500 | ['T015', 'T017']