## Sheet1
task_id | task_name | assigned_role | priority | time_days | budget | dependencies | Assigned_Employee | task_status
T001 | Design and Implement Database Schema | Backend Developer | High | 10 | 5000 | [] | Employee_6 | assigned
T002 | Develop User Authentication & Authorization Backend (Login, Signup, Reset Password) | Backend Developer | High | 15 | 7500 | ['T001'] | Employee_11 | assigned
T003 | Develop Core Task Management API (CRUD operations for tasks) | Backend Developer | High | 20 | 10000 | ['T001'] | Employee_15 | assigned
T004 | Develop Project and Group Management API | Backend Developer | Medium | 10 | 5000 | ['T001'] | Employee_25 | assigned
T005 | Implement Backend for Task Filtering, Sorting, and Search | Backend Developer | Medium | 10 | 5000 | ['T003'] | Employee_36 | assigned
T006 | Develop Backend for Dashboard Data Aggregation | Backend Developer | Medium | 15 | 7500 | ['T003', 'T004'] | Employee_40 | assigned
T007 | Design UI/UX for User Authentication (Login, Signup, Password Reset) | UI/UX Designer | High | 7 | 3500 | [] | Employee_30 | assigned
T008 | Design UI/UX for Task CRUD and Assignment | UI/UX Designer | High | 10 | 5000 | [] | Employee_31 | assigned
T009 | Design UI/UX for Project/Group Management | UI/UX Designer | Medium | 5 | 2500 | [] | Employee_32 | assigned
T010 | Design UI/UX for Overall and Personalized Dashboards | UI/UX Designer | Medium | 8 | 4000 | [] | Employee_39 | assigned
T011 | Develop Frontend for User Authentication Pages | Frontend Developer | High | 10 | 5000 | ['T002', 'T007'] | Employee_5 | assigned
T012 | Develop Frontend for Task Creation, Viewing, Editing, and Assignment | Frontend Developer | High | 15 | 7500 | ['T003', 'T008'] | Employee_10 | assigned
T013 | Develop Frontend for Task Filtering, Sorting, and Search | Frontend Developer | Medium | 7 | 3500 | ['T005', 'T008'] | Employee_12 | assigned
T014 | Develop Frontend for Project/Group Management | Frontend Developer | Medium | 8 | 4000 | ['T004', 'T009'] | Employee_26 | assigned
T015 | Develop Frontend for Overall and Personalized Dashboards | Frontend Developer | Medium | 12 | 6000 | ['T006', 'T010'] | Employee_45 | assigned
T016 | Setup Development, Staging, and Production Environments | DevOps Engineer | High | 10 | 5000 | [] | Employee_9 | assigned
T017 | Implement CI/CD Pipeline for Automated Deployment | DevOps Engineer | Medium | 8 | 4000 | ['T016'] | Employee_19 | assigned
T018 | Implement Security Measures & Data Privacy Compliance (GDPR, CCPA) | Backend Developer | High | 10 | 5000 | ['T002', 'T003'] | Employee_42 | assigned
T019 | Develop and Execute Unit/Integration Tests for Backend APIs | QA Engineer | High | 15 | 7500 | ['T002', 'T003', 'T004', 'T005', 'T006'] | Merin | assigned
T020 | Develop and Execute End-to-End Tests for Frontend | QA Engineer | High | 15 | 7500 | ['T011', 'T012', 'T013', 'T014', 'T015'] | Employee_20 | assigned
T021 | Conduct System Performance and Scalability Testing | QA Engineer | Medium | 10 | 5000 | ['T017'] | Employee_22 | assigned
T022 | Coordinate and Facilitate User Acceptance Testing | QA Engineer | High | 7 | 3500 | ['T019', 'T020', 'T021'] | Employee_23 | assigned