## Sheet1
task_id | task_name | assigned_role | priority | time_days | budget | dependencies | assigned_empl | task_status | start_date | end_date | assigned_email | project_manager | project_manager_email | RACI
T001 | Design and Implement Database Schema | Backend Developer | High | 10 | 5000 | [] | Employee_6 | assigned | 2026-05-05 | 2026-05-19 | smilnatherese@gmail.com | Anas | anasanax321@gmail.com | R
T002 | Develop User Authentication & Authorization Backend (Login, Signup, Reset Password) | Backend Developer | High | 15 | 7500 | ['T001'] | Employee_11 | assigned | 2026-05-20 | 2026-06-10 | neha26biju@gmail.com | Anas | anasanax321@gmail.com | R
T003 | Develop Core Task Management API (CRUD operations for tasks) | Backend Developer | High | 20 | 10000 | ['T001'] | Employee_15 | assigned | 2026-06-11 | 2026-07-09 | anasanax321@gmail.com | Anas | anasanax321@gmail.com | R
T004 | Develop Project and Group Management API | Backend Developer | Medium | 10 | 5000 | ['T001'] | Employee_25 | assigned | 2026-07-10 | 2026-07-24 | merin.baiju123@gmail.com | Anas | anasanax321@gmail.com | R
T005 | Implement Backend for Task Filtering, Sorting, and Search | Backend Developer | Medium | 10 | 5000 | ['T003'] | Employee_36 | assigned | 2026-07-27 | 2026-08-10 | smilnatherese@gmail.com | Anas | anasanax321@gmail.com | R
T006 | Develop Backend for Dashboard Data Aggregation | Backend Developer | Medium | 15 | 7500 | ['T003', 'T004'] | Employee_40 | assigned | 2026-08-11 | 2026-09-01 | naveenmanu369@gmail.com | Anas | anasanax321@gmail.com | R
T007 | Design UI/UX for User Authentication (Login, Signup, Password Reset) | UI/UX Designer | High | 7 | 3500 | [] | Employee_30 | assigned | 2026-09-02 | 2026-09-11 | smilnatherese@gmail.com | Anas | anasanax321@gmail.com | R
T008 | Design UI/UX for Task CRUD and Assignment | UI/UX Designer | High | 10 | 5000 | [] | Employee_31 | assigned | 2026-09-14 | 2026-09-28 | anasanax321@gmail.com | Anas | anasanax321@gmail.com | R
T009 | Design UI/UX for Project/Group Management | UI/UX Designer | Medium | 5 | 2500 | [] | Employee_32 | assigned | 2026-09-29 | 2026-10-06 | naveenmanu369@gmail.com | Anas | anasanax321@gmail.com | R
T010 | Design UI/UX for Overall and Personalized Dashboards | UI/UX Designer | Medium | 8 | 4000 | [] | Employee_39 | assigned | 2026-10-07 | 2026-10-19 | anasanax321@gmail.com | Anas | anasanax321@gmail.com | R
T011 | Develop Frontend for User Authentication Pages | Frontend Developer | High | 10 | 5000 | ['T002', 'T007'] | Employee_5 | assigned | 2026-10-20 | 2026-11-03 | ranjithnair011@gmail.com | Anas | anasanax321@gmail.com | R
T012 | Develop Frontend for Task Creation, Viewing, Editing, and Assignment | Frontend Developer | High | 15 | 7500 | ['T003', 'T008'] | Employee_10 | assigned | 2026-11-04 | 2026-11-25 | neha26diya@gmail.com | Anas | anasanax321@gmail.com | R
T013 | Develop Frontend for Task Filtering, Sorting, and Search | Frontend Developer | Medium | 7 | 3500 | ['T005', 'T008'] | Employee_12 | assigned | 2026-11-26 | 2026-12-07 | smilnatherese@gmail.com | Anas | anasanax321@gmail.com | R
T014 | Develop Frontend for Project/Group Management | Frontend Developer | Medium | 8 | 4000 | ['T004', 'T009'] | Employee_26 | assigned | 2026-12-08 | 2026-12-18 | neha26diya@gmail.com | Anas | anasanax321@gmail.com | R
T015 | Develop Frontend for Overall and Personalized Dashboards | Frontend Developer | Medium | 12 | 6000 | ['T006', 'T010'] | Employee_45 | assigned | 2026-12-21 | 2027-01-06 | ranjithnair011@gmail.com | Anas | anasanax321@gmail.com | R
T016 | Setup Development, Staging, and Production Environments | DevOps Engineer | High | 10 | 5000 | [] | Employee_9 | assigned | 2027-01-07 | 2027-01-21 | merin.baiju123@gmail.com | Anas | anasanax321@gmail.com | R
T017 | Implement CI/CD Pipeline for Automated Deployment | DevOps Engineer | Medium | 8 | 4000 | ['T016'] | Employee_19 | assigned | 2027-01-22 | 2027-02-03 | neha26biju@gmail.com | Anas | anasanax321@gmail.com | R
T018 | Implement Security Measures & Data Privacy Compliance (GDPR, CCPA) | Backend Developer | High | 10 | 5000 | ['T002', 'T003'] | Employee_42 | assigned | 2027-02-04 | 2027-02-18 | neha26diya@gmail.com | Anas | anasanax321@gmail.com | R
T019 | Develop and Execute Unit/Integration Tests for Backend APIs | QA Engineer | High | 15 | 7500 | ['T002', 'T003', 'T004', 'T005', 'T006'] | Merin | assigned | 2027-02-19 | 2027-03-12 | merin.baiju123@gmail.com | Anas | anasanax321@gmail.com | R
T020 | Develop and Execute End-to-End Tests for Frontend | QA Engineer | High | 15 | 7500 | ['T011', 'T012', 'T013', 'T014', 'T015'] | Employee_20 | assigned | 2027-03-15 | 2027-04-05 | smilnatherese@gmail.com | Anas | anasanax321@gmail.com | R
T021 | Conduct System Performance and Scalability Testing | QA Engineer | Medium | 10 | 5000 | ['T017'] | Employee_22 | assigned | 2027-04-06 | 2027-04-20 | smilnatherese@gmail.com | Anas | anasanax321@gmail.com | R
T022 | Coordinate and Facilitate User Acceptance Testing | QA Engineer | High | 7 | 3500 | ['T019', 'T020', 'T021'] | Employee_23 | assigned | 2027-04-21 | 2027-04-30 | anasanax321@gmail.com | Anas | anasanax321@gmail.com | R