## Sheet1
task_id | task_name | assigned_role | priority | time_days | budget | dependencies | Assigned_Employee | task_status
SRMS_001 | Project Kick-off & Requirement Analysis Refinement | Project Manager | High | 5 | 2000 | [] | Anas | assigned
SRMS_002 | Database Design and Schema Implementation | Backend Developer | High | 15 | 6000 | ['SRMS_001'] | Employee_43 | assigned
SRMS_003 | Backend API Development - User Management (CRUD, Role-based Access Control) | Backend Developer | High | 10 | 4000 | ['SRMS_002'] | Employee_53 | assigned
SRMS_004 | Backend API Development - Student Management (Add, Edit, Delete, Assign to classes) | Backend Developer | High | 8 | 3200 | ['SRMS_002'] | Employee_54 | assigned
SRMS_005 | Backend API Development - Course/Subject Management (Add, Edit, Delete, Assign teachers) | Backend Developer | Medium | 7 | 2800 | ['SRMS_002'] | Employee_67 | assigned
SRMS_006 | Backend API Development - Marks Entry (Teacher input, different grading schemes) | Backend Developer | High | 12 | 4800 | ['SRMS_004', 'SRMS_005'] | Employee_75 | assigned
SRMS_007 | Backend API Development - Result Processing (Calculate total marks, percentages, grades, apply rules) | Backend Developer | High | 15 | 6000 | ['SRMS_006'] | Employee_85 | assigned
SRMS_008 | Frontend Development - User Interface (User, Student, Course/Subject Management) | Frontend Developer | High | 20 | 8000 | ['SRMS_003', 'SRMS_004', 'SRMS_005'] | Employee_73 | assigned
SRMS_009 | Frontend Development - Marks Entry Interface | Frontend Developer | High | 10 | 4000 | ['SRMS_006'] | Employee_78 | assigned
SRMS_010 | Backend & Frontend Development - Report Generation (Grade cards, summaries, trends, export) | Fullstack Developer | High | 25 | 10000 | ['SRMS_007', 'SRMS_008'] | Arjun Mathew | assigned
SRMS_011 | Backend & Frontend Development - Performance Analysis Dashboard | Fullstack Developer | Medium | 18 | 7200 | ['SRMS_007', 'SRMS_008'] | No Resource Available | waiting_resource
SRMS_012 | Data Security Implementation (Encryption, Vulnerability Protection, Access Control) & Audit Trails | Security Engineer | High | 10 | 5000 | ['SRMS_003', 'SRMS_007'] | Employee_205 | assigned
SRMS_013 | System Integration Testing & User Acceptance Testing (UAT) | QA Engineer | High | 15 | 6000 | ['SRMS_009', 'SRMS_010', 'SRMS_011'] | Employee_37 | assigned
SRMS_014 | Deployment, Infrastructure Setup & Monitoring (Cloud-based, Scalability) | DevOps Engineer | High | 7 | 3500 | ['SRMS_001'] | Employee_24 | assigned
SRMS_015 | Documentation & User Training Material Preparation | Technical Writer | Medium | 10 | 3000 | ['SRMS_013'] | Employee_206 | assigned